## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Thesis Paper Reading (5 papers) | 1 | 6 | 1 | 6 | 100%
Milestone 1: Research Topic Selection | 6 | 1 | 6 | 1 | 100%
Thesis Paper Reading (15 papers) | 6 | 15 | 6 | 15 | 100%
Milestone 2: Research Proposal Writing/Submission | 6 | 16 | 6 | 16 | 100%
Additional Thesis Paper Reading (25 papers) | 22 | 14 |  |  | 0%
Milestone 3: Interim Report Writing/Submission | 22 | 14 |  |  | 0%
Additional Thesis Paper Reading (25 papers) | 36 | 19 |  |  | 0%
Develop MVP | 36 | 14 |  |  | 0%
MVP: Data Collection | 36 | 3 |  |  | 0%
MVP: Data Preprocessing & Cleaning | 39 | 2 |  |  | 0%
MVP: Implement Sentiment Analyser | 41 | 3 |  |  | 0%
MVP: Incorporate DRL ( RL+LSTM) | 44 | 3 |  |  | 0%
MVP: Evalution and Interpretation of model | 47 | 5 |  |  | 0%
Milestone 4: Final Dissertation Report & Video | 36 | 25 |  |  | 0%
Final Milestone: Completion of Final Thesis | 55 | 60 |  |  | 0%